## Communication Calendar
Enforcement ID | Enforcement / Release Name | System / API | Owner | Enforcement Date | Original Announcement (T-4 weeks) | Follow-Up 1 (T-3 weeks) | Follow-Up 2 (T-2 weeks) | Follow-Up 3 (T-1 week) | Final Notice (Enforcement week) | Days Until Enforcement | Status | Notes
AP-001 | Spectral Governance — JSON Field Naming | API Marketplace/SmartBear | Kusum Lata/API Program team | 2026-08-01 | 2026-07-04 | 2026-07-11 | 2026-07-18 | 2026-07-25 | 2026-07-31 | 26 | In Progress | Dual-name support ends at cutover
AP-002 | [Next change name] | [System] | [Owner] | [7 empty] | Not Started
AP-003 | [Next change name] | [System] | [Owner] | [7 empty] | Not Started
Formulas:
Original Announcement (T-4 weeks) = IF([Enforcement Date]="","",[Enforcement Date]-28)
Follow-Up 1 (T-3 weeks) = IF([Enforcement Date]="","",[Enforcement Date]-21)
Follow-Up 2 (T-2 weeks) = IF([Enforcement Date]="","",[Enforcement Date]-14)
Follow-Up 3 (T-1 week) = IF([Enforcement Date]="","",[Enforcement Date]-7)
Final Notice (Enforcement week) = IF([Enforcement Date]="","",[Enforcement Date]-1)
Days Until Enforcement = IF([Enforcement Date]="","",[Enforcement Date]-TODAY())